## Project Tracking
GIS Project Plan / Tracker
Estimated Project Duration : 4 weeks + 2weeks(buffer) |  |  |  | Soft Deadline | 15th April
|  |  |  | Hard Deadline | 26th April
* Weeks run from Monday to Saturday .
** Sunday is reserved for summarising and next week planning.
Deliverable(s)
Status | Deadline | Task | Assignee | Description | Deliverable | % Done | Est. Hrs | Actual Hrs
Week 0 | 14-18th March | Prepare Dataset
 | 2017-03-18 | Clean BMTC dataset |  | details of task here |  | 0%
 | 2017-03-18 | Scrap Metro Data |  |  |  | 0%
☐ | 2017-03-18 | Clean and Prepare Final Dataset |  |  |  | 0%
Week 1 | 20-25th March | Transporatation Network Modelling
☐ | 2017-03-25
☐ | 2017-03-25
☐ | 2017-03-25 | Brainstorming on Routing Algo : A* / Genetic Algo
☐
Week 2 | 27-1st April | Implementing Routing Algo
☐ | 2017-04-01
☐
☐
☐
Week 3 | 3-7th April | Building API
☐ | 2017-04-08
☐ | 2017-04-08
☐ | 2017-04-08
☐
Week 4 | 10-15th April | Running project on AWS
2017-04-15